## Sheet1
Completion Time
This spreadsheet demonstrates using simulation analysis to estimate project completion time. Given a | [6 empty] | Mean Time |  | #NAME?
series of sequential tasks, and estimates for Optimistic (o), Expected (m) and Pessimistic (p) time to | [6 empty] | Median Time |  | #NAME?
completion, we can estimate the probability of overall completion within the expected mean time. | [6 empty] | Mean Delay |  | #NAME?
In this analysis, time probabilities are generated directly from the three time estimates using a triangular
distribution to generate actual time at each iteration. The range of times o-m-p defines the distribution. | [6 empty] | 75% Confidence |  | #NAME?
Alternatively, specific weights could be assigned to each estimate directly (see Sheet 2).
Target Date Probability
To recalculate the results, select "Run Simulation" from the MonteCarlo Add-In menu. | [6 empty] | On Schedule (m) | 17 | #NAME?
Note: Recalculation without the MonteCarlo Add-ins will cause the #NAME! error | [6 empty] | Within 5% | 17.85 | #NAME?
The Monte Carlo Add-In for Excel | [6 empty] | Within 10% | 18.7 | #NAME?
Tasks | Time (o) | Time (m) | Time (p) | Time (s) | Mean Delay | Contribution
Totals | 12 | 17 | 23 | #NAME?
Analysis | 2 | 3 | 4 | #NAME? | #NAME? | #NAME?
Requirements | 3 | 4 | 5 | #NAME? | #NAME? | #NAME?
Development | 5 | 6 | 8 | #NAME? | #NAME? | #NAME?
Documentation | 1 | 2 | 3 | #NAME? | #NAME? | #NAME?
QA | 1 | 2 | 3 | #NAME? | #NAME? | #NAME?
[7 empty] | Completion Expected |  | Before | On
[7 empty] | -25% | 12.75 | #NAME? | #NAME?
[7 empty] | -20% | 13.6 | #NAME? | #NAME?
[7 empty] | -15% | 14.45 | #NAME? | #NAME?
[7 empty] | -10% | 15.3 | #NAME? | #NAME?
[7 empty] | -5% | 16.15 | #NAME? | #NAME?
[7 empty] | 0% | 17 | #NAME? | #NAME?
[7 empty] | 5% | 17.85 | #NAME? | #NAME?
[7 empty] | 10% | 18.7 | #NAME? | #NAME?
[7 empty] | 15% | 19.55 | #NAME? | #NAME?
[7 empty] | 20% | 20.4 | #NAME? | #NAME?
[7 empty] | 25% | 21.25 | #NAME? | #NAME?

## Sheet2
Completion Time
This speadsheet adds weights for each time estimate to generate the time at each iteration. Times are | [10 empty] | Mean Time |  | #NAME?
generated using a uniform probability function. In this example, weights are given with a total value of 1, | [10 empty] | Median Time |  | #NAME?
although any sum value could be used. | [10 empty] | Mean Delay |  | #NAME?
A uniform random value (R) is generated for each row. The time is selected based on the weights of the row. The | [10 empty] | 75% Confidence |  | #NAME?
value of this variable and the weights are used to generate the simulation time T(s). The distribution of T(s) over all
iterations of the simulation is used to determine the likelihood of completion on time and within certain tolerances. | [10 empty] | Target Date Probability
[11 empty] | On Schedule (m) | 17 | #NAME?
Tasks | T(o) | T(m) | T(p) | W(o) | W(m) | W(p) | R | Time (s) | Mean Delay | Contribution | Within 5% | 17.85 | #NAME?
[11 empty] | Within 10% | 18.7 | #NAME?
Totals | 12 | 17 | 23 |  |  |  |  | #NAME?
Analysis | 2 | 3 | 4 | 0.1 | 0.5 | 0.4 | #NAME? | #NAME? | #NAME? | #NAME?
Requirements | 3 | 4 | 5 | 0.2 | 0.5 | 0.3 | #NAME? | #NAME? | #NAME? | #NAME?
Development | 5 | 6 | 8 | 0.45 | 0.5 | 0.05 | #NAME? | #NAME? | #NAME? | #NAME?
Documentation | 1 | 2 | 3 | 0.6 | 0.25 | 0.15 | #NAME? | #NAME? | #NAME? | #NAME?
QA | 1 | 2 | 3 | 0.3 | 0.5 | 0.2 | #NAME? | #NAME? | #NAME? | #NAME?
[11 empty] | Completion Expected |  | Before | On
[11 empty] | -25% | 12.75 | #NAME? | #NAME?
[11 empty] | -20% | 13.6 | #NAME? | #NAME?
[11 empty] | -15% | 14.45 | #NAME? | #NAME?
[11 empty] | -10% | 15.3 | #NAME? | #NAME?
[11 empty] | -5% | 16.15 | #NAME? | #NAME?
[11 empty] | 0% | 17 | #NAME? | #NAME?
[11 empty] | 5% | 17.85 | #NAME? | #NAME?
[11 empty] | 10% | 18.7 | #NAME? | #NAME?
[11 empty] | 15% | 19.55 | #NAME? | #NAME?
[11 empty] | 20% | 20.4 | #NAME? | #NAME?
[11 empty] | 25% | 21.25 | #NAME? | #NAME?