## Schedule
YOUR TITLE HERE
PROPOSED SCHEDULE
CLIENT | [12 empty] | 2026-07-29
PROJECT
ORDER No
ADDITIONAL DATA
START DATE / FINISH DATE | 2003-07-10 |  | 2004-07-20 |  | 2026-07-29
REVISION | v 2
TASK SCHEDULER
TASK | SCHEDULED START | No OF DAYS FOR TASK | SCHEDULED FINISH | FORCAST % COMPLETE | FORCAST DAYS COMPLETE | ACTUAL % COMPLETE | ACTUAL DAYS COMPLETE |  |  | SCHD No OF DAYS FOR TASK | ACTUAL No OF DAYS INTO TASK | % OF OVERALL
[12 empty] | TIME FOR TASK |  |  | SCHEDULED START | ACTUAL DAYS COMPLETE | FORCAST DAYS COMPLETE | No OF DAYS FOR TASK
ORDER AWARD | 2003-07-10 | 2 | 2003-07-11 | 100% | 2 |  | 0 | 2003-07-10 | 2003-07-10 | 1 | 0 | 1.333% | 5.0133 | ORDER AWARD | 2003-07-10 | 0 | 2 | 0
DOCUMENTATION | 2003-07-12 | 30 | 2003-08-10 | 100% | 30 |  | 0 | 2003-07-12 | 2003-07-12 | 14 | 0 | 18.67% | 70.1867 | DOCUMENTATION | 2003-07-12 | 0 | 30 | 0
DRAWING SUBMISSION | 2003-08-11 | 2 | 2003-08-12 | 100% | 2 |  | 0 | 2003-08-11 | 2003-08-11 | 1 | 0 | 1.333% | 5.0133 | DRAWING SUBMISSION | 2003-08-11 | 0 | 2 | 0
DRAWING APPROVAL | 2003-08-13 | 15 | 2003-08-27 | 100% | 15 |  | 0 | 2003-08-13 | 2003-08-13 | 7 | 0 | 9.333% | 35.0933 | DRAWING APPROVAL | 2003-08-13 | 0 | 15 | 0
CERTIFIED DRAWINGS | 2003-08-28 | 30 | 2003-09-26 | 100% | 30 |  | 0 | 2003-08-28 | 2003-08-28 | 14 | 0 | 18.67% | 70.1867 | CERTIFIED DRAWINGS | 2003-08-28 | 0 | 30 | 0
EQUIPMENT MANUFACTURE | 2003-09-27 | 80 | 2003-12-15 | 100% | 80 |  | 0 | 2003-09-27 | 2003-09-27 | 37 | 0 | 49.33% | 185.4933 | EQUIPMENT MANUFACTURE | 2003-09-27 | 0 | 80 | 0
STEEL FABRICATION | 2003-12-16 | 80 | 2004-03-04 | 100% | 80 |  | 0 | 2003-12-16 | 2003-12-16 | 37 | 0 | 49.33% | 185.4933 | STEEL FABRICATION | 2003-12-16 | 0 | 80 | 0
ASSEMBLE | 2004-03-05 | 20 | 2004-03-24 | 100% | 20 |  | 0 | 2004-03-05 | 2004-03-05 | 9 | 0 | 12% | 45.12 | ASSEMBLE | 2004-03-05 | 0 | 20 | 0
SURFACE TREATMENT | 2004-03-25 | 17 | 2004-04-10 | 100% | 17 |  | 0 | 2004-03-25 | 2004-03-25 | 8 | 0 | 10.67% | 40.1067 | SURFACE TREATMENT | 2004-03-25 | 0 | 17 | 0
FINAL INSPECTION | 2004-04-11 | 9 | 2004-04-19 | 100% | 9 |  | 0 | 2004-04-11 | 2004-04-11 | 4 | 0 | 5.333% | 20.0533 | FINAL INSPECTION | 2004-04-11 | 0 | 9 | 0
DESPATCH EX WORKS | 2004-04-20 | 4 | 2004-04-23 | 100% | 4 |  | 0 | 2004-04-20 | 2004-04-20 | 2 | 0 | 2.667% | 10.0267 | DESPATCH EX WORKS | 2004-04-20 | 0 | 4 | 0
ANTICIPATED SITE DELIVERY | 2004-04-24 | 7 | 2004-04-30 | 100% | 7 |  | 0 | 2004-04-24 | 2004-04-24 | 10 | 0 | 13.33% | 50.1333 | ANTICIPATED SITE DELIVERY | 2004-04-24 | 0 | 7 | 0
VENDOR ITEMS, MTRS ETC | 2004-05-01 | 80 | 2004-07-19 | 100% | 80 |  | 0 | 2004-05-01 | 2004-05-01 | 37 | 0 | 49.33% | 185.4933 | VENDOR ITEMS, MTRS ETC | 2004-05-01 | 0 | 80 | 0
[10 empty] | 75 |  | 100% | 376
Formulas:
SCHEDULED FINISH = [SCHEDULED START]+[No OF DAYS FOR TASK]-1

## Gantt Chart
PROPOSED SCHEDULE
CLIENT
PROJECT
ORDER No
TASK DURATION
FORCAST COMPLETE
ACTUAL COMPLETE