## Macros Disabled
DEFAULT SCREEN
This screen is displayed during FILE SAVE or if macros were DISABLED on file open
MACROS MUST BE ENABLED TO USE THIS PROGRAM
Click Here for Enable Macros Directions
EasyProjectPlan©
Licensed to: DEMO USER 1 (NOT LICENSED FOR COMMERCIAL OR PERSONAL USE)

## EasyProjectPlan© (hidden)
Level | % | Status | Flag | Task | Start | Finish | WBS Predecessors | Outline Level EasyProjectPlan© | Dependent EasyProjectPlan© | Unique ID EasyProjectPlan© | Outlook EasyProjectPlan© | Summary EasyProjectPlan© | Reserved_2 EasyProjectPlan© | Owner | Priority | Milestone | Notes | Custom Column 1 | Custom Column 2 | Custom Column 3
1 Summary |  |  |  | Initiation | 2015-01-01 08:00 | 2015-02-18 17:00 |  | 1 |  | DEMOProjectName_1 |  | Yes |  | Owner1,Owner2,Owner3
1 Task | 100% | COMPLETED |  | Collect project ideas | 2015-01-01 08:00 | 2015-01-01 09:00 |  | 2 |  | DEMOProjectName_2 |  | No |  | Owner1 |  |  | Double-Click Task or Note Cell to Edit | 1 hr | 2 hr | 1/1/2006
1 Task | 100% | COMPLETED | O | Prioritize project ideas | 2015-01-02 08:00 | 2015-01-05 09:45 | 1.1 | 2 | DEMOProjectName_2 | DEMOProjectName_3 |  | No |  | Owner2 | CRITICAL | Yes |  | 3 hrs | 4 hrs | 1/2/2006
1 Task | 100% | COMPLETED |  | Gather customer requirements | 2015-01-05 08:00 | 2015-01-05 11:30 | 1.2 | 2 | DEMOProjectName_3 | DEMOProjectName_4 |  | No |  | Owner3 |  |  | Mouse Right-Click to Edit/Insert Hyperlinks | 5 hrs | 6 hrs | 1/3/2006
1 Task | 100% | COMPLETED |  | Select and justify a project | 2015-01-06 08:00 | 2015-01-06 15:45 | 1.3 | 2 | DEMOProjectName_4 | DEMOProjectName_5 |  | No |  | Owner1,Owner2
1 Task | 100% | COMPLETED | O | Submit and approve the Request for Proposal | 2015-01-08 08:00 | 2015-01-08 17:00 | 1.2,1.3,1.4 | 2 | DEMOProjectName_3,DEMOProjectName_4,DEMOProjectName_5 | DEMOProjectName_6 |  | No |  | Owner1,Owner3 | H
1 Task | 10% | BEHIND SCHEDULE |  | Identify the project sponsor and project manager | 2015-02-09 08:00 | 2015-02-11 10:00 | 1.5 | 2 | DEMOProjectName_6 | DEMOProjectName_7 |  | No |  | Owner2,Owner3
1 Task | 20% | BEHIND SCHEDULE | O | Get the project team in place | 2015-01-07 08:00 | 2015-01-08 12:00 | 1.6 | 2 | DEMOProjectName_7 | DEMOProjectName_8 |  | No |  | Owner1,Owner2,Owner3 | M
1 Task | 30% | ON SCHEDULE |  | Prepare the Requirements Document | 2015-01-09 08:00 | 2015-01-19 17:00 | 1.7[FS+2 days] | 2 | DEMOProjectName_8[FS+2 days] | DEMOProjectName_9 |  | No |  | Owner1,Owner2,Owner3
1 Task | 40% | DATE TBD |  | Conduct project kickoff meeting |  | 2015-02-09 17:00 |  | 2 |  | DEMOProjectName_10 |  | No |  | Owner1,Owner2,Owner3 | L
1 Task | 50% | CANCELLED |  | Conduct project brainstorming meeting |  |  |  | 2 |  | DEMOProjectName_11 |  | No |  | Owner1,Owner2,Owner3
1 Task | 60% | ON SCHEDULE |  | Develop Statement of Scope | 2015-01-09 08:00 | 2015-02-11 17:00 | 1.5,1.6,1.7,1.8 | 2 | DEMOProjectName_6,DEMOProjectName_7,DEMOProjectName_8,DEMOProjectName_9 | DEMOProjectName_12 |  | No |  | Owner1,Owner2,Owner3 | NONE | Yes
2 Summary |  |  |  | WBS Development | 2015-01-09 08:00 | 2015-02-16 17:00 | 1.13 | 2 | DEMOProjectName_17 | DEMOProjectName_13 |  | Yes |  | Owner1,Owner2,Owner3
2 Task | 70% | ON SCHEDULE |  | Conduct Work Breakdown Structure meeting | 2015-01-09 08:00 | 2015-02-13 17:00 |  | 3 |  | DEMOProjectName_14 |  | No |  | Owner1,Owner2,Owner3 | ?
2 Task | 80% | ON SCHEDULE |  | Build Work Breakdown Structure (WBS) | 2015-01-14 08:00 | 2015-02-16 17:00 |  | 3 |  | DEMOProjectName_15 |  | No |  | Owner1,Owner2,Owner3
2 Task | 90% | ON SCHEDULE |  | Update WBS in Project Plan | 2015-01-15 08:00 | 2015-02-16 17:00 |  | 3 |  | DEMOProjectName_16 |  | No |  | Owner1,Owner2,Owner3
1 Task | 100% | COMPLETED |  | Outline project plan | 2015-01-16 08:00 | 2015-02-18 17:00 |  | 2 |  | DEMOProjectName_17 |  | No |  | Owner1,Owner2,Owner3
1 Task | 100% | COMPLETED |  | Assign resources to project plan tasks | 2015-01-16 08:00 | 2015-02-18 17:00 |  | 2 |  | DEMOProjectName_18 |  | No |  | Owner1,Owner2,Owner3
1 Summary |  |  |  | Analysis | 2015-01-16 08:00 | 2015-02-23 17:00 | 1 | 1 | DEMOProjectName_1 | DEMOProjectName_19 |  | Yes |  | Owner1,Owner2,Owner3
1 Task | 0% | FUTURE TASK |  | Create Entity Relationship Diagram | 2015-01-16 08:00 | 2015-02-19 17:00 |  | 2 |  | DEMOProjectName_20 |  | No |  | Owner1,Owner2,Owner3
1 Task | 100% | COMPLETED |  | Create Data Flow Diagram | 2015-01-16 08:00 | 2015-02-20 17:00 |  | 2 |  | DEMOProjectName_21 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0% | FUTURE TASK |  | Define data dictionary | 2015-01-21 08:00 | 2015-02-23 17:00 |  | 2 |  | DEMOProjectName_22 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0% | FUTURE TASK |  | Perform object-oriented analysis | 2015-01-22 08:00 | 2015-02-23 17:00 |  | 2 |  | DEMOProjectName_23 |  | No |  | Owner1,Owner2,Owner3
1 Summary |  |  |  | Design | 2015-01-23 08:00 | 2015-03-06 17:00 | 2 | 1 | DEMOProjectName_19 | DEMOProjectName_24 |  | Yes |  | Owner1,Owner2,Owner3
1 Task | 0% | FUTURE TASK |  | Design data model | 2015-01-23 08:00 | 2015-02-25 17:00 |  | 2 |  | DEMOProjectName_25 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0% | FUTURE TASK |  | Write functional specifications | 2015-01-23 08:00 | 2015-02-25 17:00 |  | 2 |  | DEMOProjectName_26 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0% | FUTURE TASK |  | Design storyboards and/or prototypes | 2015-01-23 08:00 | 2015-02-26 17:00 |  | 2 |  | DEMOProjectName_27 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0% | FUTURE TASK |  | Write detailed design specifications | 2015-01-23 08:00 | 2015-02-27 17:00 |  | 2 |  | DEMOProjectName_28 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0% | FUTURE TASK |  | Write documentation plan | 2015-01-28 08:00 | 2015-03-02 17:00 |  | 2 |  | DEMOProjectName_29 |  | No |  | Owner1,Owner2,Owner3
1 Task | 100% | COMPLETED |  | Write beta test plan | 2015-01-29 08:00 | 2015-03-02 17:00 |  | 2 |  | DEMOProjectName_30 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0% | FUTURE TASK |  | Write SQA test plan | 2015-01-30 08:00 | 2015-03-04 17:00 |  | 2 |  | DEMOProjectName_31 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0% | FUTURE TASK |  | Write SQA test cases | 2015-01-30 08:00 | 2015-03-04 17:00 |  | 2 |  | DEMOProjectName_32 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0% | FUTURE TASK |  | Write customer support plan | 2015-01-30 08:00 | 2015-03-04 17:00 |  | 2 |  | DEMOProjectName_33 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0% | FUTURE TASK |  | Write training plan | 2015-01-30 08:00 | 2015-03-05 17:00 |  | 2 |  | DEMOProjectName_34 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0% | FUTURE TASK |  | Write risk management plan | 2015-01-30 08:00 | 2015-03-06 17:00 |  | 2 |  | DEMOProjectName_35 |  | No |  | Owner1,Owner2,Owner3
1 Summary |  |  |  | Development | 2015-02-05 08:00 | 2015-03-12 17:00 |  | 1 |  | DEMOProjectName_36 |  | Yes |  | Owner1,Owner2,Owner3
1 Task | 0% | FUTURE TASK |  | Code application components | 2015-02-05 08:00 | 2015-03-09 17:00 |  | 2 |  | DEMOProjectName_37 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0% | FUTURE TASK |  | Unit test | 2015-02-06 08:00 | 2015-03-11 17:00 |  | 2 |  | DEMOProjectName_38 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0% | FUTURE TASK |  | Integration test | 2015-02-06 08:00 | 2015-03-11 17:00 |  | 2 |  | DEMOProjectName_39 |  | No |  | Owner1,Owner2,Owner3
1 Task | 100% | COMPLETED |  | Write documentation | 2015-02-06 08:00 | 2015-03-11 17:00 |  | 2 |  | DEMOProjectName_40 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0% | FUTURE TASK |  | Write training courseware | 2015-02-06 08:00 | 2015-03-12 17:00 |  | 2 |  | DEMOProjectName_41 |  | No |  | Owner1,Owner2,Owner3
1 Summary |  |  |  | Software Quality Assurance (SQA) | 2015-02-11 08:00 | 2015-03-18 17:00 |  | 1 |  | DEMOProjectName_42 |  | Yes |  | Owner1,Owner2,Owner3
1 Task | 0% | FUTURE TASK |  | System test | 2015-02-11 08:00 | 2015-03-16 17:00 |  | 2 |  | DEMOProjectName_43 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0% | FUTURE TASK |  | Track defects | 2015-02-12 08:00 | 2015-03-16 17:00 |  | 2 |  | DEMOProjectName_44 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0% | FUTURE TASK |  | Regression test | 2015-02-13 08:00 | 2015-03-18 17:00 |  | 2 |  | DEMOProjectName_45 |  | No |  | Owner1,Owner2,Owner3
1 Summary |  |  |  | Manage Release and Change | 2015-02-13 08:00 | 2015-03-23 17:00 |  | 1 |  | DEMOProjectName_46 |  | Yes |  | Owner1,Owner2,Owner3
1 Task | 0% | FUTURE TASK |  | Configuration management | 2015-02-13 08:00 | 2015-03-18 17:00 |  | 2 |  | DEMOProjectName_47 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0% | FUTURE TASK |  | New full releases | 2015-02-13 08:00 | 2015-03-19 17:00 |  | 2 |  | DEMOProjectName_48 |  | No |  | Owner1,Owner2,Owner3
1 Task | 100% | COMPLETED |  | Maintenance releases | 2015-02-13 08:00 | 2015-03-20 17:00 |  | 2 |  | DEMOProjectName_49 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0% | FUTURE TASK |  | Defect and enhancement tracking | 2015-02-18 08:00 | 2015-03-23 17:00 |  | 2 |  | DEMOProjectName_50 |  | No |  | Owner1,Owner2,Owner3
1 Summary |  |  |  | Implementation | 2015-02-20 08:00 | 2015-04-03 17:00 |  | 1 |  | DEMOProjectName_51 |  | Yes |  | Owner1,Owner2,Owner3
1 Task | 0% | FUTURE TASK |  | Install beta test system | 2015-02-20 08:00 | 2015-03-25 17:00 |  | 2 |  | DEMOProjectName_52 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0% | FUTURE TASK |  | Conduct beta tests | 2015-02-20 08:00 | 2015-03-25 17:00 |  | 2 |  | DEMOProjectName_53 |  | No |  | Owner1,Owner2,Owner3
1 Task | 100% | COMPLETED |  | Track defects and report to customer support | 2015-02-20 08:00 | 2015-03-25 17:00 |  | 2 |  | DEMOProjectName_54 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0% | FUTURE TASK |  | Gather requirements for customizations | 2015-02-20 08:00 | 2015-03-26 17:00 |  | 2 |  | DEMOProjectName_55 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0% | FUTURE TASK |  | Analysis (gap between customizations & "vanilla") | 2015-02-20 08:00 | 2015-03-27 17:00 |  | 2 |  | DEMOProjectName_56 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0% | FUTURE TASK |  | Design | 2015-02-25 08:00 | 2015-03-30 17:00 |  | 2 |  | DEMOProjectName_57 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0% | FUTURE TASK |  | Install development system (GA release) | 2015-02-26 08:00 | 2015-03-30 17:00 |  | 2 |  | DEMOProjectName_58 |  | No |  | Owner1,Owner2,Owner3
1 Task | 100% | COMPLETED |  | Implement/adapt Software | 2015-02-27 08:00 | 2015-04-01 17:00 |  | 2 |  | DEMOProjectName_59 |  | No |  | Owner1,Owner2,Owner3
1 Task | 100% | COMPLETED |  | Unit test adaptations | 2015-02-27 08:00 | 2015-04-01 17:00 |  | 2 |  | DEMOProjectName_60 |  | No |  | Owner1,Owner2,Owner3
1 Task | 100% | COMPLETED |  | Integration test (Implementation) | 2015-02-27 08:00 | 2015-04-01 17:00 |  | 2 |  | DEMOProjectName_61 |  | No |  | Owner1,Owner2,Owner3
1 Task | 100% | COMPLETED |  | Execute customer acceptance test procedure | 2015-02-27 08:00 | 2015-04-02 17:00 |  | 2 |  | DEMOProjectName_62 |  | No |  | Owner1,Owner2,Owner3
1 Task | 100% | COMPLETED |  | Cutover development to production (pilot) | 2015-02-27 08:00 | 2015-04-03 17:00 |  | 2 |  | DEMOProjectName_63 |  | No |  | Owner1,Owner2,Owner3
Note on G8: Fri 2/13/15 8:00 AM [ORIGINAL VALUE] Mon 2/9/15 8:00 AM [Owner Mon 2/2/09 12:47:17 PM]
Note on H8: Wed 2/25/15 10:00 AM [ORIGINAL VALUE] Wed 2/11/15 10:00 AM [Owner Mon 2/2/09 12:47:41 PM]

## REFERENCES (hidden)
Level | % | Status | Flag | WBS | Task | Start | Finish | Duration | WBS Predecessors | Outline Level EasyProjectPlan© | Dependent EasyProjectPlan© | Unique ID EasyProjectPlan© | Outlook EasyProjectPlan© | Summary EasyProjectPlan© | Reserved_2 EasyProjectPlan© | Owner | Priority | Milestone | Notes | Custom Column 1 | Custom Column 2 | Custom Column 3
1 Summary |  |  |  |  | Initiation | 2015-01-01 08:00 | 2015-02-18 17:00 |  |  | 1 |  | DEMOProjectName_1 |  | Yes |  | Owner1,Owner2,Owner3
1 Task | 1 | COMPLETED |  |  | Collect project ideas | 2015-01-01 08:00 | 2015-01-01 09:00 |  |  | 2 |  | DEMOProjectName_2 |  | No |  | Owner1 |  |  | Double-Click Task or Note Cell to Edit | 1 hr | 2 hr | 1/1/2006
1 Task | 1 | COMPLETED | O |  | Prioritize project ideas | 2015-01-02 08:00 | 2015-01-05 09:45 |  | 1.1 | 2 | DEMOProjectName_2 | DEMOProjectName_3 |  | No |  | Owner2 | CRITICAL | Yes |  | 3 hrs | 4 hrs | 1/2/2006
1 Task | 1 | COMPLETED |  |  | Gather customer requirements | 2015-01-05 08:00 | 2015-01-05 11:30 |  | 1.2 | 2 | DEMOProjectName_3 | DEMOProjectName_4 |  | No |  | Owner3 |  |  | Mouse Right-Click to Edit/Insert Hyperlinks | 5 hrs | 6 hrs | 1/3/2006
1 Task | 1 | COMPLETED |  |  | Select and justify a project | 2015-01-06 08:00 | 2015-01-06 15:45 |  | 1.3 | 2 | DEMOProjectName_4 | DEMOProjectName_5 |  | No |  | Owner1,Owner2
1 Task | 1 | COMPLETED | O |  | Submit and approve the Request for Proposal | 2015-01-08 08:00 | 2015-01-08 17:00 |  | 1.2,1.3,1.4 | 2 | DEMOProjectName_3,DEMOProjectName_4,DEMOProjectName_5 | DEMOProjectName_6 |  | No |  | Owner1,Owner3 | H
1 Task | 0.1 | BEHIND SCHEDULE |  |  | Identify the project sponsor and project manager | 2015-02-09 08:00 | 2015-02-11 10:00 |  | 1.5 | 2 | DEMOProjectName_6 | DEMOProjectName_7 |  | No |  | Owner2,Owner3
1 Task | 0.2 | BEHIND SCHEDULE | O |  | Get the project team in place | 2015-01-07 08:00 | 2015-01-08 12:00 |  | 1.6 | 2 | DEMOProjectName_7 | DEMOProjectName_8 |  | No |  | Owner1,Owner2,Owner3 | M
1 Task | 0.3 | ON SCHEDULE |  |  | Prepare the Requirements Document | 2015-01-09 08:00 | 2015-01-19 17:00 |  | 1.7[FS+2 days] | 2 | DEMOProjectName_8[FS+2 days] | DEMOProjectName_9 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0.4 | DATE TBD |  |  | Conduct project kickoff meeting |  | 2015-02-09 17:00 |  |  | 2 |  | DEMOProjectName_10 |  | No |  | Owner1,Owner2,Owner3 | L
1 Task | 0.5 | CANCELLED |  |  | Conduct project brainstorming meeting |  |  |  |  | 2 |  | DEMOProjectName_11 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0.6 | ON SCHEDULE |  |  | Develop Statement of Scope | 2015-01-09 08:00 | 2015-02-11 17:00 |  | 1.5,1.6,1.7,1.8 | 2 | DEMOProjectName_6,DEMOProjectName_7,DEMOProjectName_8,DEMOProjectName_9 | DEMOProjectName_12 |  | No |  | Owner1,Owner2,Owner3 | NONE | Yes
2 Summary |  |  |  |  | WBS Development | 2015-01-09 08:00 | 2015-02-16 17:00 |  | 1.13 | 2 | DEMOProjectName_17 | DEMOProjectName_13 |  | Yes |  | Owner1,Owner2,Owner3
2 Task | 0.7 | ON SCHEDULE |  |  | Conduct Work Breakdown Structure meeting | 2015-01-09 08:00 | 2015-02-13 17:00 |  |  | 3 |  | DEMOProjectName_14 |  | No |  | Owner1,Owner2,Owner3 | ?
2 Task | 0.8 | ON SCHEDULE |  |  | Build Work Breakdown Structure (WBS) | 2015-01-14 08:00 | 2015-02-16 17:00 |  |  | 3 |  | DEMOProjectName_15 |  | No |  | Owner1,Owner2,Owner3
2 Task | 0.9 | ON SCHEDULE |  |  | Update WBS in Project Plan | 2015-01-15 08:00 | 2015-02-16 17:00 |  |  | 3 |  | DEMOProjectName_16 |  | No |  | Owner1,Owner2,Owner3
1 Task | 1 | COMPLETED |  |  | Outline project plan | 2015-01-16 08:00 | 2015-02-18 17:00 |  |  | 2 |  | DEMOProjectName_17 |  | No |  | Owner1,Owner2,Owner3
1 Task | 1 | COMPLETED |  |  | Assign resources to project plan tasks | 2015-01-16 08:00 | 2015-02-18 17:00 |  |  | 2 |  | DEMOProjectName_18 |  | No |  | Owner1,Owner2,Owner3
1 Summary |  |  |  |  | Analysis | 2015-01-16 08:00 | 2015-02-23 17:00 |  | 1 | 1 | DEMOProjectName_1 | DEMOProjectName_19 |  | Yes |  | Owner1,Owner2,Owner3
1 Task | 0 | FUTURE TASK |  |  | Create Entity Relationship Diagram | 2015-01-16 08:00 | 2015-02-19 17:00 |  |  | 2 |  | DEMOProjectName_20 |  | No |  | Owner1,Owner2,Owner3
1 Task | 1 | COMPLETED |  |  | Create Data Flow Diagram | 2015-01-16 08:00 | 2015-02-20 17:00 |  |  | 2 |  | DEMOProjectName_21 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0 | FUTURE TASK |  |  | Define data dictionary | 2015-01-21 08:00 | 2015-02-23 17:00 |  |  | 2 |  | DEMOProjectName_22 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0 | FUTURE TASK |  |  | Perform object-oriented analysis | 2015-01-22 08:00 | 2015-02-23 17:00 |  |  | 2 |  | DEMOProjectName_23 |  | No |  | Owner1,Owner2,Owner3
1 Summary |  |  |  |  | Design | 2015-01-23 08:00 | 2015-03-06 17:00 |  | 2 | 1 | DEMOProjectName_19 | DEMOProjectName_24 |  | Yes |  | Owner1,Owner2,Owner3
1 Task | 0 | FUTURE TASK |  |  | Design data model | 2015-01-23 08:00 | 2015-02-25 17:00 |  |  | 2 |  | DEMOProjectName_25 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0 | FUTURE TASK |  |  | Write functional specifications | 2015-01-23 08:00 | 2015-02-25 17:00 |  |  | 2 |  | DEMOProjectName_26 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0 | FUTURE TASK |  |  | Design storyboards and/or prototypes | 2015-01-23 08:00 | 2015-02-26 17:00 |  |  | 2 |  | DEMOProjectName_27 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0 | FUTURE TASK |  |  | Write detailed design specifications | 2015-01-23 08:00 | 2015-02-27 17:00 |  |  | 2 |  | DEMOProjectName_28 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0 | FUTURE TASK |  |  | Write documentation plan | 2015-01-28 08:00 | 2015-03-02 17:00 |  |  | 2 |  | DEMOProjectName_29 |  | No |  | Owner1,Owner2,Owner3
1 Task | 1 | COMPLETED |  |  | Write beta test plan | 2015-01-29 08:00 | 2015-03-02 17:00 |  |  | 2 |  | DEMOProjectName_30 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0 | FUTURE TASK |  |  | Write SQA test plan | 2015-01-30 08:00 | 2015-03-04 17:00 |  |  | 2 |  | DEMOProjectName_31 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0 | FUTURE TASK |  |  | Write SQA test cases | 2015-01-30 08:00 | 2015-03-04 17:00 |  |  | 2 |  | DEMOProjectName_32 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0 | FUTURE TASK |  |  | Write customer support plan | 2015-01-30 08:00 | 2015-03-04 17:00 |  |  | 2 |  | DEMOProjectName_33 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0 | FUTURE TASK |  |  | Write training plan | 2015-01-30 08:00 | 2015-03-05 17:00 |  |  | 2 |  | DEMOProjectName_34 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0 | FUTURE TASK |  |  | Write risk management plan | 2015-01-30 08:00 | 2015-03-06 17:00 |  |  | 2 |  | DEMOProjectName_35 |  | No |  | Owner1,Owner2,Owner3
1 Summary |  |  |  |  | Development | 2015-02-05 08:00 | 2015-03-12 17:00 |  |  | 1 |  | DEMOProjectName_36 |  | Yes |  | Owner1,Owner2,Owner3
1 Task | 0 | FUTURE TASK |  |  | Code application components | 2015-02-05 08:00 | 2015-03-09 17:00 |  |  | 2 |  | DEMOProjectName_37 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0 | FUTURE TASK |  |  | Unit test | 2015-02-06 08:00 | 2015-03-11 17:00 |  |  | 2 |  | DEMOProjectName_38 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0 | FUTURE TASK |  |  | Integration test | 2015-02-06 08:00 | 2015-03-11 17:00 |  |  | 2 |  | DEMOProjectName_39 |  | No |  | Owner1,Owner2,Owner3
1 Task | 1 | COMPLETED |  |  | Write documentation | 2015-02-06 08:00 | 2015-03-11 17:00 |  |  | 2 |  | DEMOProjectName_40 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0 | FUTURE TASK |  |  | Write training courseware | 2015-02-06 08:00 | 2015-03-12 17:00 |  |  | 2 |  | DEMOProjectName_41 |  | No |  | Owner1,Owner2,Owner3
1 Summary |  |  |  |  | Software Quality Assurance (SQA) | 2015-02-11 08:00 | 2015-03-18 17:00 |  |  | 1 |  | DEMOProjectName_42 |  | Yes |  | Owner1,Owner2,Owner3
1 Task | 0 | FUTURE TASK |  |  | System test | 2015-02-11 08:00 | 2015-03-16 17:00 |  |  | 2 |  | DEMOProjectName_43 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0 | FUTURE TASK |  |  | Track defects | 2015-02-12 08:00 | 2015-03-16 17:00 |  |  | 2 |  | DEMOProjectName_44 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0 | FUTURE TASK |  |  | Regression test | 2015-02-13 08:00 | 2015-03-18 17:00 |  |  | 2 |  | DEMOProjectName_45 |  | No |  | Owner1,Owner2,Owner3
1 Summary |  |  |  |  | Manage Release and Change | 2015-02-13 08:00 | 2015-03-23 17:00 |  |  | 1 |  | DEMOProjectName_46 |  | Yes |  | Owner1,Owner2,Owner3
1 Task | 0 | FUTURE TASK |  |  | Configuration management | 2015-02-13 08:00 | 2015-03-18 17:00 |  |  | 2 |  | DEMOProjectName_47 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0 | FUTURE TASK |  |  | New full releases | 2015-02-13 08:00 | 2015-03-19 17:00 |  |  | 2 |  | DEMOProjectName_48 |  | No |  | Owner1,Owner2,Owner3
1 Task | 1 | COMPLETED |  |  | Maintenance releases | 2015-02-13 08:00 | 2015-03-20 17:00 |  |  | 2 |  | DEMOProjectName_49 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0 | FUTURE TASK |  |  | Defect and enhancement tracking | 2015-02-18 08:00 | 2015-03-23 17:00 |  |  | 2 |  | DEMOProjectName_50 |  | No |  | Owner1,Owner2,Owner3
1 Summary |  |  |  |  | Implementation | 2015-02-20 08:00 | 2015-04-03 17:00 |  |  | 1 |  | DEMOProjectName_51 |  | Yes |  | Owner1,Owner2,Owner3
1 Task | 0 | FUTURE TASK |  |  | Install beta test system | 2015-02-20 08:00 | 2015-03-25 17:00 |  |  | 2 |  | DEMOProjectName_52 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0 | FUTURE TASK |  |  | Conduct beta tests | 2015-02-20 08:00 | 2015-03-25 17:00 |  |  | 2 |  | DEMOProjectName_53 |  | No |  | Owner1,Owner2,Owner3
1 Task | 1 | COMPLETED |  |  | Track defects and report to customer support | 2015-02-20 08:00 | 2015-03-25 17:00 |  |  | 2 |  | DEMOProjectName_54 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0 | FUTURE TASK |  |  | Gather requirements for customizations | 2015-02-20 08:00 | 2015-03-26 17:00 |  |  | 2 |  | DEMOProjectName_55 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0 | FUTURE TASK |  |  | Analysis (gap between customizations & "vanilla") | 2015-02-20 08:00 | 2015-03-27 17:00 |  |  | 2 |  | DEMOProjectName_56 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0 | FUTURE TASK |  |  | Design | 2015-02-25 08:00 | 2015-03-30 17:00 |  |  | 2 |  | DEMOProjectName_57 |  | No |  | Owner1,Owner2,Owner3
1 Task | 0 | FUTURE TASK |  |  | Install development system (GA release) | 2015-02-26 08:00 | 2015-03-30 17:00 |  |  | 2 |  | DEMOProjectName_58 |  | No |  | Owner1,Owner2,Owner3
1 Task | 1 | COMPLETED |  |  | Implement/adapt Software | 2015-02-27 08:00 | 2015-04-01 17:00 |  |  | 2 |  | DEMOProjectName_59 |  | No |  | Owner1,Owner2,Owner3
1 Task | 1 | COMPLETED |  |  | Unit test adaptations | 2015-02-27 08:00 | 2015-04-01 17:00 |  |  | 2 |  | DEMOProjectName_60 |  | No |  | Owner1,Owner2,Owner3
1 Task | 1 | COMPLETED |  |  | Integration test (Implementation) | 2015-02-27 08:00 | 2015-04-01 17:00 |  |  | 2 |  | DEMOProjectName_61 |  | No |  | Owner1,Owner2,Owner3
1 Task | 1 | COMPLETED |  |  | Execute customer acceptance test procedure | 2015-02-27 08:00 | 2015-04-02 17:00 |  |  | 2 |  | DEMOProjectName_62 |  | No |  | Owner1,Owner2,Owner3
1 Task | 1 | COMPLETED |  |  | Cutover development to production (pilot) | 2015-02-27 08:00 | 2015-04-03 17:00 |  |  | 2 |  | DEMOProjectName_63 |  | No |  | Owner1,Owner2,Owner3

## DATA (hidden)
ON SCHEDULE |  |  |  | 1 Summary | 1 | FALSE |  | OLD RISK COMMENTS | DEMOProjectName | FALSE | Version Expiration | Track Changes | Task Color | LastName, FirstName | Toolbar buttons | Date Format | Outlook Sync | Version History | [Owner Thu 6/11/09 10:46:01 AM] | Use SyncID *REMOVED* | Levels | Project Info | Green COMPLETED | Require Summary to have task | 26. Viewer | 27. Column Names | 28. Export | 29. Time Format | 30. Duration Days/Hr/Min | 31.Resource Manager | 32.Flag Color | 33. Move Weekend dates | 34. Custom Columns | Baseline Work | 36. Import/Export CUSTOM columns | 37. FILE MODE | 38. SCHEDULE TASKS | 39. OUTLOOK TASK DETAILS | 40. English Warning | QUICK START | 42. File Links | 43. Zoom/Freeze | RESERVED FOR USERNAME | What is the Impact of this Task on the Project Schedule?
FUTURE TASK | CRITICAL | Yes | 0% | 1 Task |  | 232004999902934 | UPDATE REQUEST FOR |  | 63 | FALSE | FALSE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | TRUE |  | TRUE | 2 | ON SCHEDULE | TRUE | FALSE | FALSE | % | Template 1 (Project Viewer) | TRUE | TRUE | TRUE | FALSE | FALSE | 21 | Actual Work | FALSE | EPP | TRUE | FALSE | TRUE | www.EasyProjectPlan.com | TRUE | TRUE |  | A problem will cause the project to fail
COMPLETED | H |  | 10% | 2 Summary | DEMO USER 1 (NOT LICENSED FOR COMMERCIAL OR PERSONAL USE) | FALSE | TRUE |  | WBS Abbreviation | FALSE | 2008-01-01 | TRUE |  | FALSE | TRUE | TRUE | TRUE |  |  |  |  | Tue 1/1/08 8:00 AM | Duration Weekend | Percent Rollup | C:\Documents and Settings\Owner\Desktop\Project1.txt | Status | TRUE | 8:00 AM | FALSE | TRUE |  |  | 22 | Actual Finish | TRUE |  | TRUE | 23 | FALSE | FILE DOWNLOAD easyprojectplan.zip | TRUE | TRUE |  | A problem will require significant rescheduling
DATE TBD | M | O | 20% | 2 Task |  |  | Hi, |  | P1 | FALSE | THIS IS AN OLDER VERSION - EDITING HAS BEEN DISABLED | TRUE |  |  | FALSE |  | FALSE |  |  |  |  | Wed 4/2/08 5:00 PM | FALSE | FALSE |  | Flag |  | 5:00 PM | FALSE | TRUE |  |  | 23 | Actual Start |  |  |  | FALSE |  | EMAIL info@easyprojectplan.com |  |  |  | A problem will require some noticeable rescheduling
BEHIND SCHEDULE | L | Milestone (row 1) | 30% | 3 Summary | 12.7 Build 65 |  | The following task needs an update: |  | TRUE | FALSE | Please download the latest version or contact the Project Manager. | TRUE |  |  |  |  | FALSE |  |  |  |  | PM Name | Export_pred |  |  | WBS |  | 8 |  |  |  |  | 21 | Overallocated |  |  |  | 21 | [5 empty] | A problem can be easily adjusted in the schedule
ON HOLD | NONE | Flag (row 2) | 40% | 3 Task | TRUE |  | TRUE |  |  | FALSE | TRUE | TRUE |  |  |  |  | FALSE |  |  |  |  | My Name | FALSE |  |  | Task | [7 empty] | Free Slack |  |  |  | FALSE | [5 empty] | No impact on the project schedule
DELETED | ? |  | 50% | 4 Summary | (Week 1) |  | TRUE |  |  | FALSE |  | TRUE |  |  |  |  | FALSE |  |  |  |  | Client Name | Priority column name |  |  | Start | [7 empty] | Total Slack |  |  |  | 22
CANCELLED |  |  | 60% | 4 Task | FALSE |  | TRUE |  |  | FALSE |  | FALSE |  |  |  |  | TRUE |  |  |  |  | My Client | FALSE |  |  | Finish | [7 empty] | Remaining Duration |  |  |  | FALSE
NO REQUIREMENTS |  |  | 70% | 5 Summary |  |  | TRUE |  |  | FALSE |  | FALSE |  |  |  |  | FALSE |  |  |  |  | Project Description |  |  |  | Duration | [7 empty] | Remaining Overtime Cost |  |  |  | 24
? |  |  | 80% | 5 Task | 2009-06-11 10:46 |  | TRUE |  |  | FALSE |  | TRUE | [9 empty] | My Project Description |  |  |  | WBS Predecessors | [7 empty] | Remaining Cost |  |  |  | FALSE
|  |  | 90% | 6 Summary | IMPORT ADMIN INFO SLOT |  | TRUE |  |  | FALSE |  | FALSE | [9 empty] | Optional Field 4 |  |  |  | Owner | [7 empty] | Baseline Start |  |  |  | 25
|  |  | 100% | 6 Task | Excel 2003 |  | TRUE |  |  | FALSE |  | FALSE | [13 empty] | Priority | [7 empty] | Baseline Finish |  |  |  | FALSE
|  |  |  | 7 Summary | 1 |  | TRUE |  |  | FALSE |  | TRUE | [9 empty] | Optional Field 5 |  |  |  | Milestone | [7 empty] | CPI |  |  |  | 26
|  |  |  | 7 Task | 1 |  | TRUE |  |  | FALSE |  | FALSE | [13 empty] | Notes | [7 empty] | * |  |  |  | FALSE
|  |  |  | 8 Summary | 1033 |  | TRUE |  |  |  |  | TRUE | [9 empty] | Optional Field 6 | [11 empty] | * |  |  |  | FALSE
|  |  |  | 8 Task | FALSE |  | TRUE | [26 empty] | *
|  |  |  | 9 Summary | / |  | TRUE | [14 empty] | Optional Field 7 | [11 empty] | *
|  |  |  | 9 Task | . |  | TRUE | [26 empty] | *
|  |  |  | 10 Summary | , |  | TRUE | [14 empty] | Optional Field 8 | [11 empty] | *
|  |  |  | 10 Task | Windows (32-bit) NT 6.00 |  | TRUE | [26 empty] | *
|  |  |  | 11 Summary |  |  | TRUE | [14 empty] | Optional Field 9 | [11 empty] | *
|  |  |  | 11 Task |  |  | TRUE | [26 empty] | *
|  |  |  | 12 Summary |  |  | ALLOWNERS,projectmanager@yourcompany.com | [14 empty] | Optional Field 10 | [11 empty] | *
|  |  |  | 12 Task |  |  | FALSE | [26 empty] | *
|  |  |  | 13 Summary | [29 empty] | *
|  |  |  | 13 Task | [29 empty] | *
|  |  |  | 14 Summary | [29 empty] | *
|  |  |  | 14 Task | [29 empty] | *
|  |  |  | 15 Summary | [29 empty] | *
|  |  |  | 15 Task | [17 empty] | FALSE | [11 empty] | *
16 Summary
16 Task
17 Summary
17 Task
18 Summary
18 Task
19 Summary
19 Task
20 Summary
20 Task
21 Summary
21 Task
22 Summary
22 Task
23 Summary
23 Task
24 Summary
24 Task
25 Summary
25 Task
26 Summary
26 Task
27 Summary
27 Task
28 Summary
28 Task
29 Summary
29 Task
30 Summary
30 Task
31 Summary
31 Task
32 Summary
32 Task
33 Summary
33 Task
34 Summary
34 Task
35 Summary
35 Task
36 Summary
36 Task
37 Summary
37 Task
38 Summary
38 Task
39 Summary
39 Task
40 Summary
40 Task
41 Summary
41 Task
42 Summary
42 Task
43 Summary
43 Task
44 Summary
44 Task
45 Summary
45 Task
46 Summary
46 Task
47 Summary
47 Task
48 Summary
48 Task
49 Summary
49 Task
50 Summary
50 Task
51 Summary
51 Task
52 Summary
52 Task
53 Summary
53 Task
54 Summary
54 Task
55 Summary
55 Task
56 Summary
56 Task
57 Summary
57 Task
58 Summary
58 Task
59 Summary
59 Task
60 Summary
60 Task
61 Summary
61 Task
62 Summary
62 Task
63 Summary
63 Task
64 Summary
64 Task
65 Summary
65 Task
66 Summary
66 Task

## DATA_2 (hidden)
Owner1
Owner2
Owner3

## DATA_3_OWNERS (hidden)
Owner1
Owner2
Owner3